## Sheet1
Flex ID: | 1546933
Project Totals | [8 empty] | 4/27/2026 |  |  |  | 5/4/2026 |  |  |  | 5/11/2026 |  |  |  | 5/18/2026
Staff Class | Employee Name | Total Original Budgeted Hours | Forecasted Hours to Date | Actual Hours to Date | Total ETC Hours Remaining | Total Projected Hours | Variance of Actual to Forecasted to Date | Variance of Total Projected to Original Budget | Actual Hours | Forecast Hours | Variance of Actual to Forecasted Hours | Variance of Actual to Forecasted % | Actual Hours | Forecast Hours | Variance of Actual to Forecasted Hours | Variance of Actual to Forecasted % | Actual Hours | Forecast Hours | Variance of Actual to Forecasted Hours | Variance of Actual to Forecasted % | Actual Hours | Forecast Hours | Variance of Actual to Forecasted Hours | Variance of Actual to Forecasted %
-> Staff Class : Partner
Partner | Chris Beiswenger | 16.8 | 12.8 | 0 | 8 | 8 | -12.8 | -8.8 | 0 | 0.8 | -0.8 | -100% | 0 | 4 | -4 | -100% | 0 | 4 | -4 | -100% | 0 | 4 | -4 | -100%
Partner | Gurminder Sandhu | 42 | 32 | 28 | 20 | 48 | -4 | 6 | 5 | 2 | 3 | 150% | 11 | 10 | 1 | 10% | 12 | 10 | 2 | 20% | 0 | 10 | -10 | -100%
Partner | Jeffrey Briner | 92.8 | 70.8 | 76.8 | 46 | 98.8 | 6 | 6 | 4.8 | 4.8 | 0 | 0% | 24 | 22 | 2 | 9.091% | 24 | 22 | 2 | 9.091% | 24 | 22 | 2 | 9.091%
Partner | Kevin Morris | 100.8 | 76.8 | 70 | 48 | 96 | -6.8 | -4.8 | 0 | 4.8 | -4.8 | -100% | 24 | 24 | 0 | 0% | 24 | 24 | 0 | 0% | 22 | 24 | -2 | -8.333%
Partner | Matthew Comte | 8.4 | 6.4 | 8 | 4 | 12 | 1.6 | 3.6 | 0 | 0.4 | -0.4 | -100% | 8 | 2 | 6 | 300% | 0 | 2 | -2 | -100% | 0 | 2 | -2 | -100%
Partner | Nilotpal Pegu | 100.8 | 76.8 | 64.4 | 48 | 89.4 | -12.4 | -11.4 | 0 | 4.8 | -4.8 | -100% | 23 | 24 | -1 | -4.167% | 18.4 | 24 | -5.6 | -23.33% | 23 | 24 | -1 | -4.167%
Partner | Sam Shenoy | 100.8 | 76.8 | 66.5 | 48 | 92 | -10.3 | -8.8 | 0 | 4.8 | -4.8 | -100% | 21.5 | 24 | -2.5 | -10.42% | 22.5 | 24 | -1.5 | -6.25% | 22.5 | 24 | -1.5 | -6.25%
|  | 462.4 | 352.4 | 313.7 | 222 | 444.2 | -38.7 | -18.2 | 9.8 | 22.4 | -12.6 | -56.2% | 111.5 | 110 | 1.5 | 1.4% | 100.9 | 110 | -9.1 | -8.3% | 91.5 | 110 | -18.5 | -16.8%
-> Staff Class : Managing Director
Managing Director | Frank Rinaldi | 134.4 | 102.4 | 102.4 | 64 | 134.4 | 0 | 0 | 6.4 | 6.4 | 0 | 0% | 32 | 32 | 0 | 0% | 32 | 32 | 0 | 0% | 32 | 32 | 0 | 0%
Managing Director | Juan Moore | 113.6 | 86.6 | 84 | 55 | 111 | -2.6 | -2.6 | 0 | 5.6 | -5.6 | -100% | 28 | 27 | 1 | 3.704% | 28 | 27 | 1 | 3.704% | 28 | 27 | 1 | 3.704%
|  | 248 | 189 | 186.4 | 119 | 245.4 | -2.6 | -2.6 | 6.4 | 12 | -5.6 | -46.7% | 60 | 59 | 1 | 1.7% | 60 | 59 | 1 | 1.7% | 60 | 59 | 1 | 1.7%
-> Staff Class : Director
Director | Brian Fernandes | 160 | 128 | 120 | 72 | 160 | -8 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Director | Eric Greer | 160 | 128 | 91 | 72 | 155 | -37 | -5 | 3 | 8 | -5 | -62.5% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 8 | 40 | -32 | -80%
Director | Islam Abdelkhalek | 160 | 128 | 96 | 72 | 136 | -32 | -24 | 0 | 8 | -8 | -100% | 32 | 40 | -8 | -20% | 32 | 40 | -8 | -20% | 32 | 40 | -8 | -20%
Director | Jan Schreiber | 160 | 128 | 110 | 72 | 158 | -18 | -2 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 38 | 40 | -2 | -5% | 24 | 40 | -16 | -40%
Director | John White | 160 | 128 | 120 | 72 | 156 | -8 | -4 | 8 | 8 | 0 | 0% | 36 | 40 | -4 | -10% | 40 | 40 | 0 | 0% | 36 | 40 | -4 | -10%
Director | Kuntal Pharas | 160 | 128 | 112 | 72 | 144 | -16 | -16 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40% | 40 | 40 | 0 | 0%
Director | Mrigesh Mandevia | 117.6 | 89.6 | 58 | 56 | 90 | -31.6 | -27.6 | 0 | 5.6 | -5.6 | -100% | 10 | 28 | -18 | -64.29% | 24 | 28 | -4 | -14.29% | 24 | 28 | -4 | -14.29%
Director | TBD-Martin Stenzig | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Director | Tejas Shah | 160 | 128 | 112 | 72 | 144 | -16 | -16 | 8 | 8 | 0 | 0% | 24 | 40 | -16 | -40% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Director | Erica Zimmerer | 0 | 0 | 31 | 0 | 31 | 31 | 31 | 0 | 0 | 0 | 0% | 31 | 0 | 31 | 100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
Director | Jeffrey Plummer | 0 | 0 | 20 | 80 | 100 | 20 | 100 | 4 | 0 | 4 | 100% | 16 | 0 | 16 | 100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
Director | Martin Stenzig | 0 | 0 | 48 | 80 | 128 | 48 | 128 | 8 | 0 | 8 | 100% | 40 | 0 | 40 | 100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
Director | Wayne Messervy | 0 | 40 | 48 | 80 | 128 | 8 | 128 | 8 | 0 | 8 | 100% | 40 | 0 | 40 | 100% | 0 | 0 | 0 | 0% | 0 | 40 | -40 | -100%
|  | 1405.6 | 1153.6 | 966 | 800 | 1530 | -187.6 | 124.4 | 63 | 69.6 | -6.6 | -9.5% | 389 | 348 | 41 | 11.8% | 278 | 348 | -70 | -20.1% | 236 | 388 | -152 | -39.2%
-> Staff Class : Senior Manager
Senior Manager | Arun Murugesan | 160 | 128 | 120 | 72 | 160 | -8 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Senior Manager | Dilraj Mann | 160 | 128 | 113 | 72 | 176 | -15 | 16 | 8 | 8 | 0 | 0% | 48 | 40 | 8 | 20% | 48 | 40 | 8 | 20% | 9 | 40 | -31 | -77.5%
Senior Manager | Dipti Ojha | 160 | 128 | 124 | 72 | 156 | -4 | -4 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 36 | 40 | -4 | -10% | 40 | 40 | 0 | 0%
Senior Manager | Divya Parambi | 160 | 128 | 132 | 74 | 164 | 4 | 4 | 6 | 8 | -2 | -25% | 44 | 40 | 4 | 10% | 40 | 40 | 0 | 0% | 42 | 40 | 2 | 5%
Senior Manager | Gargi Mishra | 160 | 128 | 136 | 72 | 168 | 8 | 8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Senior Manager | Greg Richardson | 160 | 128 | 112 | 72 | 152 | -16 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Senior Manager | Himanshu Bisla | 0 | 40 | 112 | 72 | 149 | 72 | 149 | 7 | 0 | 7 | 100% | 35 | 0 | 35 | 100% | 35 | 0 | 35 | 100% | 35 | 40 | -5 | -12.5%
Senior Manager | Jaymie Amaral | 160 | 120 | 122 | 42 | 130 | 2 | -30 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 34 | 32 | 2 | 6.25%
Senior Manager | Kaustubh Kulkarni | 160 | 128 | 136 | 72 | 168 | 8 | 8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Senior Manager | Mihir Patra | 160 | 128 | 112 | 72 | 160 | -16 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
Senior Manager | Pradeep Kumar | 160 | 128 | 136 | 72 | 168 | 8 | 8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Senior Manager | Remya Ramakrishnan | 160 | 128 | 124 | 72 | 164 | -4 | 4 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 44 | 40 | 4 | 10% | 32 | 40 | -8 | -20%
Senior Manager | Sarah Penoyer | 160 | 128 | 80 | 72 | 152 | -48 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Senior Manager | Sharon Pan | 160 | 128 | 112 | 72 | 144 | -16 | -16 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40% | 40 | 40 | 0 | 0%
Senior Manager | Sukanya Doshi | 160 | 128 | 0 | 72 | 72 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Senior Manager | TBD-Dustin Fichter | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
Senior Manager | TBD-Jeff Plummer | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Senior Manager | TBD-Ken Lundeen | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Senior Manager | TBD-PwC352-Onshore-Rupam Chatterjee | 160 | 128 | 0 | 0 | 0 | -128 | -160 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Senior Manager | TBD-Wayne Messervy | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
|  | 3072 | 2384 | 1671 | 1132 | 2363 | -713 | -709 | 85 | 152 | -67 | -44.1% | 567 | 760 | -193 | -25.4% | 547 | 760 | -213 | -28% | 440 | 712 | -272 | -38.2%
-> Staff Class : Manager
Manager | Afeera Haque | 160 | 128 | 113 | 72 | 169 | -15 | 9 | 8 | 8 | 0 | 0% | 47 | 40 | 7 | 17.5% | 42 | 40 | 2 | 5% | 16 | 40 | -24 | -60%
Manager | Alan Dsilva | 160 | 128 | 98 | 72 | 139 | -30 | -21 | 8 | 8 | 0 | 0% | 30 | 40 | -10 | -25% | 29 | 40 | -11 | -27.5% | 31 | 40 | -9 | -22.5%
Manager | Brian Wright | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Manager | Chris Hoffman | 160 | 128 | 112 | 72 | 152 | -16 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Manager | Hema Murthy | 160 | 112 | 112 | 56 | 144 | 0 | -16 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 24 | 0 | 0%
Manager | Mic Dyson Smiles | 160 | 128 | 136 | 72 | 176 | 8 | 16 | 8 | 8 | 0 | 0% | 56 | 40 | 16 | 40% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Manager | Pankaj Dakre | 160 | 128 | 88 | 72 | 160 | -40 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Manager | Rahul Bhatia | 84 | 64 | 80 | 60 | 100 | 16 | 16 | 0 | 4 | -4 | -100% | 0 | 20 | -20 | -100% | 40 | 20 | 20 | 100% | 40 | 20 | 20 | 100%
Manager | Rahul Sabbani | 160 | 128 | 120 | 72 | 152 | -8 | -8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0%
Manager | Tulika Das | 160 | 128 | 136 | 72 | 168 | 8 | 8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Manager | Uday Kumbhar | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Manager | Dustin Fichter | 0 | 40 | 48 | 80 | 128 | 8 | 128 | 8 | 0 | 8 | 100% | 40 | 0 | 40 | 100% | 0 | 0 | 0 | 0% | 0 | 40 | -40 | -100%
Manager | Elizabeth Harrop | 126 | 96 | 0 | 60 | 60 | -96 | -66 | 0 | 6 | -6 | -100% | 0 | 30 | -30 | -100% | 0 | 30 | -30 | -100% | 0 | 30 | -30 | -100%
Manager | TBD- Michael Randle | 160 | 128 | 0 | 72 | 72 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Manager | Zachary Franchett | 113.4 | 86.4 | 0 | 54 | 54 | -86.4 | -59.4 | 0 | 5.4 | -5.4 | -100% | 0 | 27 | -27 | -100% | 0 | 27 | -27 | -100% | 0 | 27 | -27 | -100%
|  | 2083.4 | 1678.4 | 1299 | 1030 | 1994 | -379.4 | -89.4 | 80 | 103.4 | -23.4 | -22.6% | 453 | 517 | -64 | -12.4% | 423 | 517 | -94 | -18.2% | 335 | 541 | -206 | -38.1%
-> Staff Class : Senior Associate
Senior Associate | Annie Laughlin | 160 | 128 | 136 | 72 | 170 | 8 | 10 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 38 | 40 | -2 | -5%
Senior Associate | Azucena Alegria | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Senior Associate | Connor Hanson | 160 | 128 | 120 | 72 | 160 | -8 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Senior Associate | Frances Lawley | 160 | 128 | 144 | 72 | 176 | 16 | 16 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Senior Associate | Heather Mikols | 160 | 128 | 111 | 76 | 143 | -17 | -17 | 10 | 8 | 2 | 25% | 20 | 40 | -20 | -50% | 37 | 40 | -3 | -7.5% | 44 | 40 | 4 | 10%
Senior Associate | Jerin Martin | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Senior Associate | Jie Sun | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Senior Associate | Jonathan Schermer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
Senior Associate | Luke Springer | 160 | 128 | 95.5 | 72 | 143.5 | -32.5 | -16.5 | 8 | 8 | 0 | 0% | 36 | 40 | -4 | -10% | 27.5 | 40 | -12.5 | -31.25% | 24 | 40 | -16 | -40%
Senior Associate | Maddy Barrett | 160 | 128 | 112 | 72 | 160 | -16 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
Senior Associate | Mike McGinniss | 160 | 128 | 120 | 72 | 160 | -8 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Senior Associate | Neelima Nallamothu | 160 | 128 | 136 | 72 | 168 | 8 | 8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Senior Associate | Nicholas Palmisano | 160 | 120 | 104 | 64 | 136 | -16 | -24 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40% | 32 | 32 | 0 | 0%
Senior Associate | Sam Dolan | 160 | 128 | 144 | 72 | 176 | 16 | 16 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Senior Associate | TBD-EXT-PwC557-SDM - Data | 84 | 44 | 0 | 0 | 0 | -44 | -84 | 0 | 4 | -4 | -100% | 0 | 20 | -20 | -100% | 0 | 20 | -20 | -100% | 0 | 0 | 0 | 0%
Senior Associate | TBD-PwC553-SDM - Middleware Integration Build Support | 160 | 128 | 0 | 0 | 0 | -128 | -160 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Senior Associate | Zach Lofties | 160 | 128 | 112 | 72 | 160 | -16 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
Senior Associate | Chad Moore | 160 | 128 | 88 | 72 | 160 | -40 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Senior Associate | Cynara Kidwell | 160 | 128 | 45 | 72 | 117 | -83 | -43 | 8 | 8 | 0 | 0% | 37 | 40 | -3 | -7.5% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Senior Associate | Harold Wagner | 160 | 128 | 88 | 72 | 160 | -40 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Senior Associate | Praveen Kumar | 160 | 128 | 89 | 72 | 161 | -39 | 1 | 5 | 8 | -3 | -37.5% | 44 | 40 | 4 | 10% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
|  | 3124 | 2468 | 2028.5 | 1292 | 2830.5 | -439.5 | -293.5 | 143 | 156 | -13 | -8.3% | 697 | 780 | -83 | -10.6% | 648.5 | 780 | -131.5 | -16.9% | 490 | 752 | -262 | -34.8%
-> Staff Class : Staff - Experienced
Staff - Experienced | Aastha Devkota | 160 | 128 | 120 | 72 | 160 | -8 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Staff - Experienced | Alexa Burns | 160 | 128 | 136 | 72 | 168 | 8 | 8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0%
Staff - Experienced | Caitlin Dodson | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Staff - Experienced | Caitlin Nguyen | 160 | 128 | 116 | 72 | 148 | -12 | -12 | 8 | 8 | 0 | 0% | 36 | 40 | -4 | -10% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0%
Staff - Experienced | Chloe Thill | 160 | 128 | 136 | 72 | 168 | 8 | 8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Staff - Experienced | Jordan Raye Santos | 160 | 128 | 120 | 32 | 120 | -8 | -40 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Staff - Experienced | Joseph Madrigal | 160 | 128 | 112 | 72 | 160 | -16 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
Staff - Experienced | Lily Dolliff | 160 | 120 | 112 | 64 | 144 | -8 | -16 | 8 | 8 | 0 | 0% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0% | 32 | 32 | 0 | 0%
Staff - Experienced | Nawal Abdinur | 160 | 128 | 109 | 72 | 144 | -19 | -16 | 0 | 8 | -8 | -100% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0% | 37 | 40 | -3 | -7.5%
Staff - Experienced | Nia Spicer | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Staff - Experienced | Sana Tipnis | 160 | 128 | 136 | 72 | 168 | 8 | 8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Staff - Experienced | Shivani Makadia | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0%
Staff - Experienced | Taylor Miller | 160 | 120 | 112 | 32 | 112 | -8 | -48 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20% | 32 | 32 | 0 | 0%
|  | 2080 | 1648 | 1593 | 848 | 1972 | -55 | -108 | 96 | 104 | -8 | -7.7% | 500 | 520 | -20 | -3.8% | 488 | 520 | -32 | -6.2% | 469 | 504 | -35 | -6.9%
-> Staff Class : Staff
Staff | Helen Crawford | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Staff | Jatin Chadha | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Staff | Kaley Chong | 160 | 128 | 120 | 57.6 | 145.6 | -8 | -14.4 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
Staff | Nikita Mei | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
Staff | Pearson Kurka | 160 | 128 | 128 | 72 | 160 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
|  | 800 | 640 | 632 | 345.6 | 785.6 | -8 | -14.4 | 40 | 40 | 0 | 0% | 200 | 200 | 0 | 0% | 200 | 200 | 0 | 0% | 192 | 200 | -8 | -4%
-> Staff Class : AC
AC - Manager | Isha Varshney | 0 | 80 | 88 | 80 | 168 | 8 | 168 | 8 | 0 | 8 | 100% | 40 | 0 | 40 | 100% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
AC - Senior | NAMBI KRISHNAN P | 0 | 80 | 112 | 80 | 168 | 32 | 168 | 8 | 0 | 8 | 100% | 40 | 0 | 40 | 100% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Senior Managing Director | Amar Anay Pendse | 117.6 | 89.6 | 78 | 56 | 132 | -11.6 | 14.4 | 4 | 5.6 | -1.6 | -28.57% | 40 | 28 | 12 | 42.86% | 32 | 28 | 4 | 14.29% | 2 | 28 | -26 | -92.86%
AC Director | Joydip Gupta | 168 | 128 | 116 | 80 | 160 | -12 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 36 | 40 | -4 | -10%
AC Senior Manager | Abhishek Sawant | 168 | 128 | 154 | 80 | 194 | 26 | 26 | 4 | 8 | -4 | -50% | 54 | 40 | 14 | 35% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior Manager | Amrita Goswami | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior Manager | Dipti Mukesh Sejpal | 168 | 128 | 96 | 80 | 168 | -32 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 8 | 40 | -32 | -80%
AC Senior Manager | Hermon Abisheak Retnamony | 168 | 128 | 67 | 80 | 127 | -61 | -41 | 0 | 8 | -8 | -100% | 22 | 40 | -18 | -45% | 25 | 40 | -15 | -37.5% | 20 | 40 | -20 | -50%
AC Senior Manager | Himanshu Bisla | 160 | 88 | 0 | 0 | 0 | -88 | -160 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Senior Manager | Nisha Shrivansh | 168 | 128 | 112 | 80 | 160 | -16 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior Manager | Pallavi Kale | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior Manager | Prasanna Nadgouda | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior Manager | Rajesh Goruputi | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior Manager | Ravikumar Rathinasamy | 168 | 128 | 120 | 80 | 168 | -8 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior Manager | Santhoshematha Kattekola | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior Manager | Sunita Sharma | 168 | 128 | 144 | 80 | 184 | 16 | 16 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior Manager | Sushil Sancheti | 168 | 128 | 118 | 72 | 158 | -10 | -10 | 0 | 8 | -8 | -100% | 46 | 40 | 6 | 15% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior Manager | TBD-PwC495-Content Mgmt - Development Team member | 21 | 16 | 0 | 0 | 0 | -16 | -21 | 0 | 1 | -1 | -100% | 0 | 5 | -5 | -100% | 0 | 5 | -5 | -100% | 0 | 5 | -5 | -100%
AC Senior Manager | Tushar Singh | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior Manager | Venkat Nadella | 168 | 128 | 80 | 80 | 160 | -48 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
AC - Non-equity Owned -Manager | Hundre, Sadhana Narayan | 168 | 48 | 0 | 0 | 0 | -48 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC Manager | Akash Parikh | 168 | 48 | 56 | 0 | 56 | 8 | -112 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 16 | 0 | 16 | 100% | 0 | 0 | 0 | 0%
AC Manager | Anamika Sharma | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Manager | Anshuman Bera | 168 | 128 | 136 | 80 | 176 | 8 | 8 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Anvesh Simhadri | 168 | 128 | 156 | 80 | 196 | 28 | 28 | 12 | 8 | 4 | 50% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Arthur Pascaran Jr. | 168 | 48 | 0 | 0 | 0 | -48 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC Manager | Asha Revanasiddappa | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Avinasha Halageri | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Basker Adithya Chiluvari | 168 | 128 | 136 | 80 | 176 | 8 | 8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Bhavanshu Mandloi | 168 | 128 | 112 | 80 | 160 | -16 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Manager | Bijaya Potnuru | 168 | 80 | 104 | 72 | 152 | 24 | -16 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Manager | Chennur Shwetha | 160 | 120 | 120 | 80 | 160 | 0 | 0 | 0 | 0 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Dhanunjai Gandavarapu | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Dilit Thakkar | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Diwakar Goud S B | 168 | 128 | 144 | 80 | 184 | 16 | 16 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Inderpreet Singh | 168 | 128 | 160 | 96 | 200 | 32 | 32 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 56 | 40 | 16 | 40%
AC Manager | Indushree N V | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Isha Varshney | 168 | 48 | 0 | 0 | 0 | -48 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC Manager | Karthik Tirumuru | 168 | 80 | 120 | 80 | 160 | 40 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Kunal Sadhukhan | 168 | 128 | 76 | 80 | 116 | -52 | -52 | 0 | 8 | -8 | -100% | 16 | 40 | -24 | -60% | 20 | 40 | -20 | -50% | 40 | 40 | 0 | 0%
AC Manager | Leena Ranje | 168 | 128 | 128 | 80 | 176 | 0 | 8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Manager | Naresh Nukala | 0 | 80 | 128 | 80 | 168 | 48 | 168 | 0 | 0 | 0 | 0% | 48 | 0 | 48 | 100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Pranabja Sahoo | 168 | 128 | 112 | 80 | 160 | -16 | -8 | 8 | 8 | 0 | 0% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Manager | Ramesh Kumar | 168 | 128 | 128 | 72 | 160 | 0 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Ramya Chandrasekaran | 168 | 128 | 104 | 80 | 160 | -24 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Manager | Sadhana Hundre | 0 | 80 | 120 | 80 | 160 | 40 | 160 | 0 | 0 | 0 | 0% | 40 | 0 | 40 | 100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Sanket Gadekar | 168 | 128 | 156 | 83 | 196 | 28 | 28 | 0 | 8 | -8 | -100% | 68 | 40 | 28 | 70% | 45 | 40 | 5 | 12.5% | 43 | 40 | 3 | 7.5%
AC Manager | Sathiya Sellamuthu | 168 | 128 | 120 | 80 | 168 | -8 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Manager | Sharath Kumar | 168 | 80 | 72 | 80 | 120 | -8 | -48 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Manager | Shobha Murugendrappa | 168 | 128 | 32 | 80 | 112 | -96 | -56 | 0 | 8 | -8 | -100% | 32 | 40 | -8 | -20% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Manager | Shrutika Chavan | 168 | 128 | 104 | 80 | 160 | -24 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Manager | Smita Singh | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Sujith Sukumar | 168 | 128 | 150 | 80 | 190 | 22 | 22 | 8 | 8 | 0 | 0% | 52 | 40 | 12 | 30% | 50 | 40 | 10 | 25% | 40 | 40 | 0 | 0%
AC Manager | Sunil Siddeswaraiah | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | Surabhi Sundram | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Manager | TBD-PwC336-EHS Reporting Analyst - Analytics (or Reporting) Analyst | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Manager | TBD-PwC356-Reporting Technical Lead - Analytics (or Reporting) Technical Lead | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Manager | TBD-PwC357-RTR/FTP Analytics (or Reporting) Analyst | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Manager | TBD-PwC497-Content Mgmt - UI / UX Developer | 84 | 64 | 0 | 0 | 0 | -64 | -84 | 0 | 4 | -4 | -100% | 0 | 20 | -20 | -100% | 0 | 20 | -20 | -100% | 0 | 20 | -20 | -100%
AC Manager | TBD-PwC570-EHS Developer | 0 | 40 | 0 | 0 | 0 | -40 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 40 | -40 | -100%
AC Manager | TBD-PwC571-Development Team member | 168 | 80 | 0 | 0 | 0 | -80 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Manager | TBD-PwC572-Development Team Member | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Manager | Vineet Ruhela | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0%
AC - Non-equity Owned -Senior | TBD-RR-2400101 | 8 | 8 | 0 | 0 | 0 | -8 | -8 | 0 | 8 | -8 | -100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC - Non-equity Owned -Senior | TBD-RR-2428382 | 48 | 0 | 0 | 0 | 0 | 0 | -48 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC Senior | Aditya Ranjan Singh | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Ahad Abdul | 168 | 128 | 136 | 80 | 176 | 8 | 8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Aniket Gharat | 168 | 128 | 136 | 80 | 176 | 8 | 8 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0%
AC Senior | ANIL G S | 168 | 128 | 120 | 72 | 152 | -8 | -16 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Ashwani Singh | 168 | 128 | 144 | 80 | 184 | 16 | 16 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Banty Gupta | 168 | 128 | 128 | 80 | 176 | 0 | 8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior | Chiranjeevii Naidu | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | DEEP SARKAR | 168 | 128 | 112 | 80 | 152 | -16 | -16 | 0 | 8 | -8 | -100% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Dharmender LNU | 168 | 128 | 112 | 80 | 160 | -16 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior | Diksha Singh | 0 | 0 | 0 | 80 | 80 | 0 | 80 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC Senior | Dinesh chowdary Batta | 0 | 80 | 120 | 80 | 160 | 40 | 160 | 0 | 0 | 0 | 0% | 24 | 0 | 24 | 100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Divya Mrinal | 168 | 128 | 112 | 43.2 | 115.2 | -16 | -52.8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0%
AC Senior | Divyanshu Tomar | 168 | 128 | 112 | 80 | 168 | -16 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Senior | Dorababu Boddu | 168 | 128 | 136 | 80 | 176 | 8 | 8 | 8 | 8 | 0 | 0% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Gaurav Virmani | 168 | 128 | 96 | 80 | 152 | -32 | -16 | 0 | 8 | -8 | -100% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Senior | Harsh Gupta | 168 | 128 | 139 | 80 | 184 | 11 | 16 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 35 | 40 | -5 | -12.5%
AC Senior | Harsha DM | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Harshavardhan Reddy Gondesi | 168 | 128 | 112 | 80 | 168 | -16 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Senior | Hemachandran K | 168 | 128 | 136 | 80 | 184 | 8 | 16 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior | Ketan Namdeo Darekar | 168 | 128 | 152 | 80 | 192 | 24 | 24 | 8 | 8 | 0 | 0% | 48 | 40 | 8 | 20% | 56 | 40 | 16 | 40% | 40 | 40 | 0 | 0%
AC Senior | L V K M Naga Devi Puvvada | 168 | 128 | 112 | 80 | 160 | -16 | -8 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 32 | 40 | -8 | -20% | 32 | 40 | -8 | -20%
AC Senior | M Shesh Sai | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Madhivannan Senathipathi | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Milan Joshi | 0 | 80 | 112 | 80 | 160 | 32 | 160 | 0 | 0 | 0 | 0% | 40 | 0 | 40 | 100% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior | Mohamad Sharif PINJARI | 168 | 128 | 120 | 80 | 168 | -8 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior | NAMBI KRISHNAN P | 168 | 48 | 0 | 0 | 0 | -48 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC Senior | Nikhil Kasar | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Senior | Nikita Khanekar | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Nikko Nitro | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Senior | Nishant Mourya | 168 | 88 | 0 | 80 | 80 | -88 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0% | 0 | 40 | -40 | -100%
AC Senior | Nishant Mourya | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 40 | 0 | 40 | 100%
AC Senior | Nitesh Agarwal | 168 | 128 | 144 | 80 | 184 | 16 | 16 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Pratik Gaikar | 0 | 40 | 0 | 80 | 80 | -40 | 80 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 40 | -40 | -100%
AC Senior | PRIYANKA CHALLA | 168 | 128 | 136 | 80 | 176 | 8 | 8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Rahul Chouhan | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Retish Purushothaman | 168 | 128 | 112 | 80 | 160 | -16 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior | Rohan Bandal | 168 | 128 | 112 | 80 | 168 | -16 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Senior | Rohan Rajendra Gupta | 168 | 128 | 64 | 80 | 104 | -64 | -64 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 24 | 40 | -16 | -40% | 40 | 40 | 0 | 0%
AC Senior | Rounak Patra | 168 | 128 | 120 | 80 | 160 | -8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Sarthak Kanodia | 168 | 128 | 128 | 72 | 160 | 0 | -8 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Sayan Mukherjee | 0 | 40 | 104 | 32 | 112 | 64 | 112 | 0 | 0 | 0 | 0% | 40 | 0 | 40 | 100% | 40 | 0 | 40 | 100% | 24 | 40 | -16 | -40%
AC Senior | Shresth Iyer | 168 | 128 | 120 | 80 | 168 | -8 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior | Shubhranta Biswas | 168 | 128 | 120 | 80 | 168 | -8 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior | Siva Sainath B V | 168 | 128 | 104 | 80 | 144 | -24 | -24 | 0 | 8 | -8 | -100% | 24 | 40 | -16 | -40% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Snehansh Jaiswal | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Sohail Mogal | 0 | 80 | 96 | 80 | 152 | 16 | 152 | 0 | 0 | 0 | 0% | 40 | 0 | 40 | 100% | 32 | 40 | -8 | -20% | 24 | 40 | -16 | -40%
AC Senior | Soukya C | 168 | 128 | 104 | 80 | 160 | -24 | -8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20% | 24 | 40 | -16 | -40%
AC Senior | Suriya C | 168 | 128 | 104 | 40 | 104 | -24 | -64 | 0 | 8 | -8 | -100% | 32 | 40 | -8 | -20% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0%
AC Senior | T Karthikeyan | 168 | 128 | 136 | 80 | 176 | 8 | 8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | Tanya Rastogi | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Senior | TBD-Kundan Shirke | 168 | 48 | 0 | 0 | 0 | -48 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC Senior | TBD-Milan Joshi | 168 | 48 | 0 | 0 | 0 | -48 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC Senior | TBD-PwC316-Quality review team member | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Senior | TBD-PwC342-HR Reporting Analyst Analytics (or Reporting) Analyst | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Senior | TBD-PwC363-SAC / DSP Analytics Developers | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Senior | TBD-PwC369-SAC / DSP Analytics Developers | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Senior | TBD-PwC371-SAC / DSP Analytics Developers | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Senior | TBD-PwC372-SAC / DSP Analytics Developers | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Senior | TBD-PwC373-SAC / DSP Analytics Developers | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Senior | TBD-PwC375-SAC / DSP Analytics Developers | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Senior | TBD-PwC376-SAC / DSP Analytics Developers | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Senior | TBD-PwC377-SAC / DSP Analytics Developers | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Senior | TBD-PwC574-Development Team Member | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Senior | TBD-PwC575-Development Team Member | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Senior | TBD-PwC576-Development Team Member | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Senior | Upendra Gorala | 168 | 128 | 112 | 80 | 160 | -16 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Senior | Vanessa Chua | 168 | 128 | 80 | 80 | 120 | -48 | -48 | 0 | 8 | -8 | -100% | 32 | 40 | -8 | -20% | 8 | 40 | -32 | -80% | 40 | 40 | 0 | 0%
AC Senior | Vishal Kumar Keshari | 168 | 128 | 96 | 80 | 144 | -32 | -24 | 0 | 8 | -8 | -100% | 32 | 40 | -8 | -20% | 32 | 40 | -8 | -20% | 32 | 40 | -8 | -20%
AC Senior | Yan Reyes | 168 | 128 | 104 | 80 | 160 | -24 | -8 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20% | 24 | 40 | -16 | -40%
AC Staff - Experienced | Abhishek Bhardwaj | 168 | 128 | 112 | 80 | 168 | -16 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Staff - Experienced | Ankit Anand | 168 | 128 | 112 | 80 | 160 | -16 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Staff - Experienced | Anurag Abnave | 168 | 128 | 136 | 80 | 176 | 8 | 8 | 8 | 8 | 0 | 0% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Staff - Experienced | Anwesha Nayak | 168 | 128 | 80 | 80 | 160 | -48 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
AC Staff - Experienced | Hari Priya Sana | 168 | 128 | 96 | 80 | 136 | -32 | -32 | 0 | 8 | -8 | -100% | 16 | 40 | -24 | -60% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Staff - Experienced | Harsh Joshi | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Staff - Experienced | Priyanka Atmaram Bedarkar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
AC Staff - Experienced | Purushothaman Kannan | 168 | 128 | 112 | 80 | 168 | -16 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 24 | 40 | -16 | -40%
AC Staff - Experienced | Ritul Saini | 168 | 128 | 128 | 80 | 168 | 0 | 0 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20% | 40 | 40 | 0 | 0%
AC Staff - Experienced | Sankrut Ananda Kumar | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Staff - Experienced | Shubh Agrawal | 168 | 128 | 104 | 80 | 176 | -24 | 8 | 8 | 8 | 0 | 0% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 8 | 40 | -32 | -80%
AC Staff - Experienced | Srutibini Das | 168 | 128 | 96 | 80 | 152 | -32 | -16 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 24 | 40 | -16 | -40% | 24 | 40 | -16 | -40%
AC Staff | Eusev Miguel Mopera | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Staff | Pratyush Kumar | 168 | 128 | 120 | 80 | 168 | -8 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 32 | 40 | -8 | -20%
AC Staff | TBD-PwC358-SAC / DSP Analytics Developers | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Staff | TBD-PwC359-SAC / DSP Analytics Developers | 168 | 128 | 0 | 0 | 0 | -128 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
AC Staff | TBD-PwC360-SAC / DSP Analytics Developers | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Staff | TBD-PwC361-SAC / DSP Analytics Developers | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Staff | TBD-PwC362-SAC / DSP Analytics Developers | 168 | 88 | 0 | 0 | 0 | -88 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0%
AC Intern | Chandana Jampally | 168 | 80 | 80 | 80 | 120 | 0 | -48 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0%
AC Intern | Sruthi Gujjula | 168 | 80 | 88 | 80 | 160 | 8 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 8 | 40 | -32 | -80%
|  | 23278.6 | 16937.6 | 12834 | 8990.2 | 18136.2 | -4103.6 | -5142.4 | 124 | 1106.6 | -982.6 | -88.8% | 4498 | 5533 | -1035 | -18.7% | 4180 | 5493 | -1313 | -23.9% | 3688 | 5093 | -1405 | -27.6%
-> Staff Class : Other
Other | Angela Castro | 42 | 32 | 27 | 20 | 41 | -5 | -1 | 2 | 2 | 0 | 0% | 10 | 10 | 0 | 0% | 9 | 10 | -1 | -10% | 6 | 10 | -4 | -40%
Other | Ananda Kumar | 0 | 0 | 192 | 0 | 192 | 192 | 192 | 48 | 0 | 48 | 100% | 94 | 0 | 94 | 100% | 50 | 0 | 50 | 100% | 0 | 0 | 0 | 0%
Other | Aniket Shelar | 0 | 0 | 88 | 0 | 88 | 88 | 88 | 0 | 0 | 0 | 0% | 48 | 0 | 48 | 100% | 40 | 0 | 40 | 100% | 0 | 0 | 0 | 0%
Other | Arjun Lahane | 168 | 48 | 0 | 0 | 0 | -48 | -168 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
Other | Chiro Chattopadhyay | 168 | 128 | 88 | 80 | 168 | -40 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Other | Esita Banerjee | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Other | Hardip Kapoor | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Other | Hardip Singh | 0 | 0 | 88 | 0 | 88 | 88 | 88 | 0 | 0 | 0 | 0% | 48 | 0 | 48 | 100% | 40 | 0 | 40 | 100% | 0 | 0 | 0 | 0%
Other | Kundan Shirke | 0 | 0 | 80 | 0 | 80 | 80 | 80 | 0 | 0 | 0 | 0% | 44 | 0 | 44 | 100% | 36 | 0 | 36 | 100% | 0 | 0 | 0 | 0%
Other | Kushal Padwal | 0 | 0 | 88 | 0 | 88 | 88 | 88 | 0 | 0 | 0 | 0% | 48 | 0 | 48 | 100% | 40 | 0 | 40 | 100% | 0 | 0 | 0 | 0%
Other | Kusum Arya | 168 | 128 | 88 | 80 | 168 | -40 | 0 | 8 | 8 | 0 | 0% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Other | Meenakshi Jha | 168 | 128 | 80 | 80 | 160 | -48 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Other | Nandini Agrawal | 168 | 128 | 80 | 80 | 160 | -48 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Other | Pratyay Saha | 168 | 128 | 80 | 80 | 160 | -48 | -8 | 0 | 8 | -8 | -100% | 40 | 40 | 0 | 0% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Other | Ritam Dutta | 168 | 128 | 224 | 80 | 304 | 96 | 136 | 48 | 8 | 40 | 500% | 112 | 40 | 72 | 180% | 64 | 40 | 24 | 60% | 0 | 40 | -40 | -100%
Other | Rupam Chatterjee | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Other | Sakshi Parashar | 168 | 128 | 88 | 80 | 168 | -40 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Other | Sudipta N Das | 0 | 0 | 240 | 0 | 240 | 240 | 240 | 48 | 0 | 48 | 100% | 112 | 0 | 112 | 100% | 80 | 0 | 80 | 100% | 0 | 0 | 0 | 0%
Other | Suparna Chakraborty | 0 | 0 | 80 | 0 | 80 | 80 | 80 | 0 | 0 | 0 | 0% | 40 | 0 | 40 | 100% | 40 | 0 | 40 | 100% | 0 | 0 | 0 | 0%
Other | Surekha Sethuram | 168 | 128 | 88 | 80 | 168 | -40 | 0 | 0 | 8 | -8 | -100% | 48 | 40 | 8 | 20% | 40 | 40 | 0 | 0% | 0 | 40 | -40 | -100%
Other | TBD-Aniket Shelar | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Other | TBD-Ashis Prusty | 0 | 40 | 0 | 80 | 80 | -40 | 80 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 40 | -40 | -100%
Other | TBD-Kushal Padwal | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Other | TBD-Nitheesh Sampath | 0 | 80 | 0 | 80 | 80 | -80 | 80 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Other | TBD-Suparna Chakroborty | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
Other | Sudipta Das | 168 | 128 | 0 | 80 | 80 | -128 | -88 | 0 | 8 | -8 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100% | 0 | 40 | -40 | -100%
|  | 2730 | 2120 | 1699 | 1380 | 3073 | -421 | 343 | 154 | 130 | 24 | 18.5% | 860 | 650 | 210 | 32.3% | 679 | 650 | 29 | 4.5% | 6 | 690 | -684 | -99.1%
|  | 39284 | 29571 | 23222.6 | 16158.8 | 33373.9 | -6348.4 | -5910.1 | 801.2 | 1896 | -1094.8 | -57.7% | 8335.5 | 9477 | -1141.5 | -12% | 7604.4 | 9437 | -1832.6 | -19.4% | 6007.5 | 9049 | -3041.5 | -33.6%